## Sheet1
Flight Controls Lab
Flight Controls Team |  |  | Project start: 8/20/25 | [14 empty] | Darker: Planned and Competed
CEO Simon Ross | CFO Aydan Vissing | [16 empty] | Lighter: Planned, Uncompleted
CTO Brady Schick | CSO Gabe Southwell | [16 empty] | Lightest: EST Plan, Uncertain
Weeks
Task | Assigned | Time (EST) | Time (ACT) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Logistics
Project Proposal | All | 2
Make Gant Chart | Aydan | 1 | bar: Weeks 3
Divide Responsability | Simon | 1
Decorate Lab Corner | All | 1 | bar: Weeks 5
Mathmatical Model | Simon & Brady | 2
Evaluate Finances | Aydan | 4 | bar: Weeks 4; Weeks 9; Weeks 16; Weeks 26
Order PCB | Simon | 1
Decide Lab Safety Measures | Aydan & Simon | 3 | bar: Weeks 20 to Weeks 22
Battery Storage Solution | Simon | 1
Software
Implement MM in Code | Gabe & Simon | 2
Drone Firmware (Basic) | Gabe & Aydan | 1 | bar: Weeks 7
Flight Code | Gabe & Aydan | 4
Implement Sensor Code | Gabe & Aydan | 3 | bar: Weeks 11 to Weeks 13
Communication Type | Gabe & Brady | 1
Altitude Calibration | Gabe & Brady | 2 | bar: Weeks 11 to Weeks 12
Simple Interface | Gabe | 3
Interactable Front End | Gabe | 3 | bar: Weeks 16 to Weeks 18
Recalibrate Sensor Code | Gabe & Aydan | 3
Recalibrate Communication | Gabe & Aydan | 3 | bar: Weeks 20 to Weeks 22
Recalibrate Altitude Control | Gabe & Aydan | 3
Recalibrate Interface | Gabe | 3 | bar: Weeks 20 to Weeks 22
GUI | Gabe | 2
Wireless Interfacing | Gabe | 2 | bar: Weeks 23 to Weeks 24
Hardware
Choose Mirocontroller | Gabe | 1
Choose Body Design | Simon | 1 | bar: Weeks 5
Power Supply System | Brady | 1
Choose Sensors | Brady & Simon | 1 | bar: Weeks 7
Get Sensors For Altitude | Gabe & Brady | 1
Decide on Motors | Gabe & Brady | 1 | bar: Weeks 7
Prototype 1 Drone Assembly | Brady & Aydan | 1
P1 Design Test & Integration | All | 4 | bar: Weeks 10 to Weeks 13
Design PCB | Brady & Simon | 3
Prototype 2 Drone Assembly | Brady & Aydan | 1 | bar: Weeks 16
P2 Design Test & Integration | All | 3
Lab Design
Drone Kit Instructions | Aydan & Simon | 2
Implement Safety Instructions | Aydan & Simon | 2 | bar: Weeks 23 to Weeks 24
Draft Software Use Guide | Gabe & Aydan | 2
Draft Lab Procedures | All | 2 | bar: Weeks 26 to Weeks 27
Lab Beta Test | All | 2 | bar: Weeks 1 to Weeks 7; Weeks 9 to Weeks 14; Weeks 16 to Weeks 24; Weeks 26 to Weeks 29
Final Drone Kit Instructions | Aydan & Simon | 2 | bar: Weeks 30 to Weeks 32
Final Safety Instructions | Aydan & Simon | 2
Final Software Use Guide | Gabe & Aydan | 2 | bar: Weeks 30 to Weeks 32
Draft Lab Procedures | All | 2